## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 | KhanhTN cannot join capstone project |  | High | SangDT | 2022-09-01 | 2022-12-05 | Closed | Team size reduce from 5 to 4 members
2 | All members have to work at the company |  | High | SangDT | 2022-09-01 | 2022-12-05 | Closed | so we can only work at night
3 | One member had difficulty during the whole project because of his bad health |  | High | SangDT | 2022-09-01 | 2022-12-05 | Closed | The group failed to meet its goal of organizing group work together one day a week

## Master
| 2022-08-28 | 2022-09-04 | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18
Training | bar: 2022-08-28 to 2022-09-25
Report 1_Project Introduction | bar: 2022-09-04 to 2022-09-11
Report 2_Project Management Plan | bar: 2022-09-18 to 2022-09-25
Report 3_Software Requirement Specification | bar: 2022-09-18 to 2022-10-09
Report 4_Software Design Document | bar: 2022-10-09 to 2022-10-23
Implementation | bar: 2022-10-09 to 2022-11-27
Report 5_Software Test Documentation | bar: 2022-10-16 to 2022-10-23
Report 5_Unit Test Document | bar: 2022-10-09 to 2022-11-27
Report 5_System Test Document | bar: 2022-10-09 to 2022-11-27
Report 6_Software User Guides | bar: 2022-11-20 to 2022-12-04
Deployment | bar: 2022-12-04
Report 7_Final Project Report | bar: 2022-12-11
Presentation Slide | bar: 2022-12-11 to 2022-12-18

## WBS
*All: all member spend time for that task
Report M | Function | Task | Estimate | P.I.C | Plan Start | Plan End | Status | Actual Start | Actual End | Actual | Diff | Deadline Of The Week | Note
Common
| Common | [10 empty] | TRUE
|  | Decide the topic | 80 | All | 2022-09-01 | 2022-09-10 | Done | 2022-09-01 | 2022-09-10 | 80 | 0 | FALSE
|  | Decide technical stacks | 10 | All | 2022-09-01 | 2022-09-10 | Done | 2022-09-01 | 2022-09-10 | 5 | -5 | FALSE
|  | Define User story | 5 | All | 2022-09-06 | 2022-09-08 | Done | 2022-09-06 | 2022-09-08 | 8 | 3 | FALSE
| Training | [10 empty] | TRUE
|  | Node Js Trainnig | 30 | All | 2022-08-21 | 2022-09-11 | Done | 2022-08-21 | 2022-09-11 | 30 | 0 | FALSE
|  | React JsTraining | 30 | All | 2022-09-11 | 2022-09-25 | Done | 2022-09-11 | 2022-09-25 | 32 | 2 | FALSE
|  | Git, Github Trainning | 5 | All | 2022-09-22 | 2022-09-25 | Done | 2022-09-22 | 2022-09-25 | 5 | 0 | FALSE
User Story | [11 empty] | TRUE
| [UC-01] Register | [10 empty] | TRUE
|  | Create wireframe & Update Screen Details(report 3) | 2 | ThanhNPN | 2022-09-25 | 2022-09-25 | Done | 2022-09-25 | 2022-09-26 | 2 | 0 | FALSE
|  | Update Feature requirement (report 3) | 3 | ThanhNPN | 2022-09-26 | 2022-09-26 | Done | 2022-09-26 | 2022-09-26 | 4 | 1 | FALSE
|  | Coding Backend | 6 | SangDT | 2022-09-23 | 2022-09-25 | Done | 2022-09-23 | 2022-09-25 | 7 | 1 | FALSE
|  | Coding Frontend | 8 | LongTT | 2022-09-23 | 2022-09-24 | Done | 2022-09-23 | 2022-09-25 | 7 | -1 | FALSE
|  | Write Unit test (Report 5) | 2 | DangHH | 2022-10-09 | 2022-10-11 | Done | 2022-10-09 | 2022-10-10 | 3 | 1 | FALSE
|  | Write Integration test (Report 5) | 3 | DangHH | 2022-10-09 | 2022-10-11 | Done | 2022-10-10 | 2022-10-11 | 3 | 0 | FALSE
| [UC-02] Log in | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 3 | ThanhNPN | 2022-09-27 | 2022-09-27 | Done | 2022-09-27 | 2022-09-27 | 3 | 0 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 2 | LongTT | 2022-09-25 | 2022-09-26 | Done | 2022-09-25 | 2022-09-26 | 3 | 1 | FALSE
|  | Coding Backend | 3 | SangDT | 2022-09-25 | 2022-09-27 | Done | 2022-09-25 | 2022-09-27 | 4 | 1 | FALSE
|  | Coding Frontend | 3 | LongTT | 2022-09-25 | 2022-09-27 | Done | 2022-09-25 | 2022-09-27 | 3 | 0 | FALSE
|  | Write Unit test (Report 5) | 3 | DangHH | 2022-10-11 | 2022-10-12 | Done | 2022-10-11 | 2022-10-12 | 3 | 0 | FALSE
|  | Write Integration test (Report 5) | 3 | DangHH | 2022-10-11 | 2022-10-12 | Done | 2022-10-11 | 2022-10-11 | 4 | 1 | FALSE
| [UC-03] Log out | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 2 | ThanhNPN | 2022-09-28 | 2022-09-28 | Done | 2022-09-28 | 2022-09-28 | 3 | 1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 2 | LongTT | 2022-09-28 | 2022-09-28 | Done | 2022-09-28 | 2022-09-28 | 2 | 0 | FALSE
|  | Coding Backend | 4 | SangDT | 2022-09-28 | 2022-09-28 | Done | 2022-09-28 | 2022-09-28 | 4 | 0 | FALSE
|  | Coding Frontend | 1 | DangHH | 2022-09-28 | 2022-09-28 | Done | 2022-09-28 | 2022-09-28 | 1 | 0 | FALSE
|  | Write Unit test (Report 5) | 2 | LongTT | 2022-10-12 | 2022-10-12 | Done | 2022-10-12 | 2022-10-12 | 2 | 0 | FALSE
|  | Write Integration test (Report 5) | 2 | DangHH | 2022-10-12 | 2022-10-12 | Done | 2022-10-12 | 2022-10-12 | 2 | 0 | FALSE
| [UC-04] Forgot password | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 3 | LongTT | 2022-09-29 | 2022-09-29 | Done | 2022-09-29 | 2022-09-29 | 4 | 1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 3 | DangHH | 2022-09-29 | 2022-09-29 | Done | 2022-09-29 | 2022-09-30 | 2 | -1 | FALSE
|  | Coding Backend | 6 | SangDT | 2022-09-29 | 2022-09-30 | Done | 2022-09-29 | 2022-09-30 | 6 | 0 | FALSE
|  | Coding Frontend | 8 | DangHH | 2022-09-29 | 2022-09-30 | Done | 2022-09-30 | 2022-10-01 | 7 | -1 | FALSE
|  | Write Unit test (Report 5) | 3 | LongTT | 2022-10-12 | 2022-10-13 | Done | 2022-10-12 | 2022-10-13 | 4 | 1 | FALSE
|  | Write Integration test (Report 5) | 3 | DangHH | 2022-10-12 | 2022-10-13 | Done | 2022-10-12 | 2022-10-13 | 3 | 0 | FALSE
| [UC-05] View products | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 4 | SangDT | 2022-09-30 | 2022-10-01 | Done | 2022-09-30 | 2022-10-31 | 5 | 1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | ThanhNPN | 2022-09-30 | 2022-10-01 | Done | 2022-10-30 | 2022-10-01 | 4 | 0 | FALSE
|  | Coding Backend | 8 | SangDT | 2022-10-01 | 2022-10-03 | Done | 2022-10-01 | 2022-10-04 | 7 | -1 | FALSE
|  | Coding Frontend | 8 | SangDT | 2022-09-30 | 2022-10-02 | Done | 2022-09-30 | 2022-10-03 | 7 | -1 | FALSE
|  | Write Unit test (Report 5) | 4 | DangHH | 2022-10-13 | 2022-10-15 | Done | 2022-10-13 | 2022-10-15 | 3 | -1 | FALSE
|  | Write Integration test (Report 5) | 4 | DangHH | 2022-10-13 | 2022-10-15 | Done | 2022-10-14 | 2022-10-14 | 3 | -1 | FALSE
| [UC-06] Search Product by Name | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 3 | LongTT | 2022-10-03 | 2022-10-04 | Done | 2022-10-03 | 2022-10-04 | 2 | -1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | SangDT | 2022-10-03 | 2022-10-04 | Done | 2022-10-04 | 2022-10-05 | 3 | -1 | FALSE
|  | Coding Backend | 6 | SangDT | 2022-10-03 | 2022-10-06 | Done | 2022-10-04 | 2022-10-05 | 7 | 1 | FALSE
|  | Coding Frontend | 3 | LongTT | 2022-10-03 | 2022-10-04 | Done | 2022-10-03 | 2022-10-05 | 2 | -1 | FALSE
|  | Write Unit test (Report 5) | 4 | DangHH | 2022-10-15 | 2022-10-15 | Done | 2022-10-15 | 2022-10-15 | 4 | 0 | FALSE
|  | Write Integration test (Report 5) | 4 | DangHH | 2022-10-15 | 2022-10-15 | Done | 2022-10-15 | 2022-10-15 | 5 | 1 | FALSE
| [UC-07] Filter product by category | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 3 | ThanhNPN | 2022-10-06 | 2022-10-07 | Done | 2022-10-06 | 2022-10-06 | 4 | 1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | LongTT | 2022-10-06 | 2022-10-07 | Done | 2022-10-06 | 2022-10-07 | 3 | -1 | FALSE
|  | Coding Backend | 8 | SangDT | 2022-10-06 | 2022-10-08 | Done | 2022-10-06 | 2022-10-08 | 7 | -1 | FALSE
|  | Coding Frontend | 6 | DangHH | 2022-10-06 | 2022-10-07 | Done | 2022-10-06 | 2022-10-08 | 7 | 1 | FALSE
|  | Write Unit test (Report 5) | 3 | DangHH | 2022-10-15 | 2022-10-16 | Done | 2022-10-15 | 2022-10-16 | 3 | 0 | FALSE
|  | Write Integration test (Report 5) | 3 | DangHH | 2022-10-15 | 2022-10-16 | Done | 2022-10-16 | 2022-10-16 | 4 | 1 | FALSE
| [UC-08] Filter product by location | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 3 | LongTT | 2022-10-08 | 2022-10-08 | Done | 2022-10-08 | 2022-10-08 | 3 | 0 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | ThanhNPN | 2022-10-08 | 2022-10-09 | Done | 2022-10-08 | 2022-10-09 | 4 | 0 | FALSE
|  | Coding Backend | 8 | SangDT | 2022-10-08 | 2022-10-10 | Done | 2022-10-08 | 2022-10-10 | 8 | 0 | FALSE
|  | Coding Frontend | 6 | DangHH | 2022-10-08 | 2022-10-10 | Done | 2022-10-08 | 2022-10-11 | 7 | 1 | FALSE
|  | Write Unit test (Report 5) | 3 | LongTT | 2022-10-16 | 2022-10-16 | Done | 2022-10-16 | 2022-10-16 | 2 | -1 | FALSE
|  | Write Integration test (Report 5) | 3 | DangHH | 2022-10-16 | 2022-10-16 | Done | 2022-10-16 | 2022-10-16 | 3 | 0 | FALSE
| [UC-09] Post product to sell | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 4 | DangHH | 2022-10-10 | 2022-10-10 | Done | 2022-10-10 | 2022-10-10 | 3 | -1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 5 | SangDT | 2022-10-10 | 2022-10-11 | Done | 2022-10-10 | 2022-10-11 | 3 | -2 | FALSE
|  | Coding Backend | 8 | ThanhNPN | 2022-10-10 | 2022-10-13 | Done | 2022-10-10 | 2022-10-13 | 9 | 1 | FALSE
|  | Coding Frontend | 8 | LongTT | 2022-10-10 | 2022-10-12 | Done | 2022-10-10 | 2022-10-12 | 9 | 1 | FALSE
|  | Write Unit test (Report 5) | 4 | LongTT | 2022-10-17 | 2022-10-20 | Done | 2022-10-17 | 2022-10-20 | 4 | 0 | FALSE
|  | Write Integration test (Report 5) | 4 | DangHH | 2022-10-17 | 2022-10-20 | Done | 2022-10-17 | 2022-10-20 | 5 | 1 | FALSE
| [UC-10] Manage Product to sell | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 4 | ThanhNPN | 2022-10-13 | 2022-10-14 | Done | 2022-10-13 | 2022-10-14 | 2 | -2 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | LongTT | 2022-10-13 | 2022-10-14 | Done | 2022-10-13 | 2022-10-14 | 2 | -2 | FALSE
|  | Coding Backend | 8 | SangDT | 2022-10-13 | 2022-10-16 | Done | 2022-10-13 | 2022-10-16 | 8 | 0 | FALSE
|  | Coding Frontend | 6 | DangHH | 2022-10-13 | 2022-10-15 | Done | 2022-10-13 | 2022-10-16 | 4 | -2 | FALSE
|  | Write Unit test (Report 5) | 3 | LongTT | 2022-10-20 | 2022-10-22 | Done | 2022-10-20 | 2022-10-22 | 4 | 1 | FALSE
|  | Write Integration test (Report 5) | 3 | DangHH | 2022-10-20 | 2022-10-22 | Done | 2022-10-22 | 2022-10-23 | 2 | -1 | FALSE
| [UC-11] Create aution | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 4 | LongTT | 2022-10-16 | 2022-10-16 | Done | 2022-10-16 | 2022-10-17 | 3 | -1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | ThanhNPN | 2022-10-16 | 2022-10-17 | Done | 2022-10-16 | 2022-10-18 | 3 | -1 | FALSE
|  | Coding Backend | 8 | SangDT | 2022-10-16 | 2022-10-19 | Done | 2022-10-16 | 2022-10-19 | 10 | 2 | FALSE
|  | Coding Frontend | 8 | DangHH | 2022-10-16 | 2022-10-17 | Done | 2022-10-16 | 2022-10-17 | 10 | 2 | FALSE
|  | Write Unit test (Report 5) | 5 | LongTT | 2022-10-22 | 2022-10-24 | Done | 2022-10-23 | 2022-10-25 | 3 | -2 | FALSE
|  | Write Integration test (Report 5) | 5 | ThanhNPN | 2022-10-22 | 2022-10-24 | Done | 2022-10-24 | 2022-10-26 | 4 | -1 | FALSE
| [UC-12] Shedule product auction | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 4 | ThanhNPN | 2022-10-19 | 2022-10-19 | Done | 2022-10-19 | 2022-10-19 | 4 | 0 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 5 | LongTT | 2022-10-19 | 2022-10-19 | Done | 2022-10-19 | 2022-10-19 | 5 | 0 | FALSE
|  | Coding Backend | 8 | SangDT | 2022-10-19 | 2022-10-23 | Done | 2022-10-19 | 2022-10-23 | 10 | 2 | FALSE
|  | Coding Frontend | 8 | LongTT | 2022-10-19 | 2022-10-23 | Done | 2022-10-19 | 2022-10-23 | 9 | 1 | FALSE
|  | Write Unit test (Report 5) | 4 | SangDT | 2022-10-24 | 2022-10-26 | Done | 2022-10-25 | 2022-10-26 | 4 | 0 | FALSE
|  | Write Integration test (Report 5) | 4 | ThanhNPN | 2022-10-24 | 2022-10-26 | Done | 2022-10-27 | 2022-10-27 | 3 | -1 | FALSE
| [UC-13] Manage auctioned product | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 4 | ThanhNPN | 2022-10-23 | 2022-10-23 | Done | 2022-10-23 | 2022-10-24 | 4 | 0 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | LongTT | 2022-10-23 | 2022-10-24 | Done | 2022-10-23 | 2022-10-24 | 4 | 0 | FALSE
|  | Coding Backend | 8 | ThanhNPN | 2022-10-23 | 2022-10-26 | Done | 2022-10-23 | 2022-10-27 | 9 | 1 | FALSE
|  | Coding Frontend | 8 | DangHH | 2022-10-23 | 2022-10-26 | Done | 2022-10-23 | 2022-10-27 | 6 | -2 | FALSE
|  | Write Unit test (Report 5) | 4 | LongTT | 2022-10-26 | 2022-10-28 | Done | 2022-10-28 | 2022-10-28 | 3 | -1 | FALSE
|  | Write Integration test (Report 5) | 4 | ThanhNPN | 2022-10-26 | 2022-10-28 | Done | 2022-10-28 | 2022-10-29 | 5 | 1 | FALSE
| [UC-14] View other user’s account information | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 3 | ThanhNPN | 2022-10-26 | 2022-10-26 | Done | 2022-10-26 | 2022-10-27 | 2 | -1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | ThanhNPN | 2022-10-26 | 2022-10-26 | Done | 2022-10-26 | 2022-10-26 | 5 | 1 | FALSE
|  | Coding Backend | 6 | SangDT | 2022-10-26 | 2022-10-28 | Done | 2022-10-26 | 2022-10-28 | 5 | -1 | FALSE
|  | Coding Frontend | 6 | DangHH | 2022-10-26 | 2022-10-28 | Done | 2022-10-26 | 2022-10-28 | 4 | -2 | FALSE
|  | Write Unit test (Report 5) | 4 | DangHH | 2022-10-28 | 2022-10-30 | Done | 2022-10-30 | 2022-10-30 | 5 | 1 | FALSE
|  | Write Integration test (Report 5) | 4 | ThanhNPN | 2022-10-28 | 2022-10-30 | Done | 2022-10-30 | 2022-10-30 | 5 | 1 | FALSE
| [UC-15] Manage order | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 4 | ThanhNPN | 2022-10-28 | 2022-10-28 | Done | 2022-10-28 | 2022-10-28 | 3 | -1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | ThanhNPN | 2022-10-28 | 2022-10-28 | Done | 2022-10-28 | 2022-10-28 | 3 | -1 | FALSE
|  | Coding Backend | 6 | SangDT | 2022-10-28 | 2022-10-30 | Done | 2022-10-28 | 2022-10-30 | 5 | -1 | FALSE
|  | Coding Frontend | 4 | SangDT | 2022-10-28 | 2022-10-30 | Done | 2022-10-28 | 2022-10-30 | 3 | -1 | FALSE
|  | Write Unit test (Report 5) | 4 | DangHH | 2022-10-30 | 2022-11-04 | Done | 2022-11-02 | 2022-11-04 | 5 | 1 | FALSE
|  | Write Integration test (Report 5) | 4 | ThanhNPN | 2022-10-30 | 2022-11-04 | Done | 2022-11-02 | 2022-11-04 | 3 | -1 | FALSE
| [UC-16] Buy product | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 4 | LongTT | 2022-10-30 | 2022-10-30 | Done | 2022-10-30 | 2022-10-30 | 3 | -1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | DangHH | 2022-10-30 | 2022-10-31 | Done | 2022-10-30 | 2022-10-31 | 3 | -1 | FALSE
|  | Coding Backend | 8 | ThanhNPN | 2022-10-30 | 2022-11-02 | Done | 2022-10-30 | 2022-11-02 | 9 | 1 | FALSE
|  | Coding Frontend | 6 | DangHH | 2022-10-30 | 2022-11-02 | Done | 2022-10-30 | 2022-11-02 | 6 | 0 | FALSE
|  | Write Unit test (Report 5) | 4 | SangDT | 2022-11-04 | 2022-11-06 | Done | 2022-11-04 | 2022-11-07 | 3 | -1 | FALSE
|  | Write Integration test (Report 5) | 4 | ThanhNPN | 2022-11-04 | 2022-11-06 | Done | 2022-11-06 | 2022-11-07 | 3 | -1 | FALSE
| [UC-17] Payment | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 2 | DangHH | 2022-11-02 | 2022-11-02 | Done | 2022-11-02 | 2022-11-02 | 1.5 | -0.5 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 2 | DangHH | 2022-11-02 | 2022-11-02 | Done | 2022-11-02 | 2022-11-02 | 2 | 0 | FALSE
|  | Coding Backend | 8 | LongTT | 2022-11-02 | 2022-11-06 | Done | 2022-11-02 | 2022-11-06 | 8 | 0 | FALSE
|  | Coding Frontend | 4 | SangDT | 2022-11-02 | 2022-11-06 | Done | 2022-11-02 | 2022-11-06 | 4 | 0 | FALSE
|  | Write Unit test (Report 5) | 3 | SangDT | 2022-11-06 | 2022-11-08 | Done | 2022-11-08 | 2022-11-09 | 3 | 0 | FALSE
|  | Write Integration test (Report 5) | 3 | ThanhNPN | 2022-11-06 | 2022-11-08 | Done | 2022-11-08 | 2022-11-09 | 2 | -1 | FALSE
| [UC-18] Add favorite product | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 2 | ThanhNPN | 2022-11-06 | 2022-11-06 | Done | 2022-11-06 | 2022-11-06 | 3 | 1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 3 | SangDT | 2022-11-06 | 2022-11-06 | Done | 2022-11-06 | 2022-11-06 | 4 | 1 | FALSE
|  | Coding Backend | 6 | LongTT | 2022-11-06 | 2022-11-08 | Done | 2022-11-06 | 2022-11-08 | 5 | -1 | FALSE
|  | Coding Frontend | 6 | DangHH | 2022-11-06 | 2022-11-08 | Done | 2022-11-06 | 2022-11-08 | 5 | -1 | FALSE
|  | Write Unit test (Report 5) | 3 | LongTT | 2022-11-08 | 2022-11-10 | Done | 2022-11-10 | 2022-11-10 | 2 | -1 | FALSE
|  | Write Integration test (Report 5) | 3 | ThanhNPN | 2022-11-08 | 2022-11-10 | Done | 2022-11-10 | 2022-11-10 | 3 | 0 | FALSE
| [UC-19] Mange favorite product list | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 3 | LongTT | 2022-11-08 | 2022-11-08 | Done | 2022-11-08 | 2022-11-08 | 2 | -1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | ThanhNPN | 2022-11-08 | 2022-11-08 | Done | 2022-11-08 | 2022-11-08 | 5 | 1 | FALSE
|  | Coding Backend | 8 | ThanhNPN | 2022-11-08 | 2022-11-11 | Done | 2022-11-08 | 2022-11-11 | 9 | 1 | FALSE
|  | Coding Frontend | 6 | DangHH | 2022-11-08 | 2022-11-11 | Done | 2022-11-08 | 2022-11-11 | 5 | -1 | FALSE
|  | Write Unit test (Report 5) | 3 | LongTT | 2022-11-10 | 2022-11-13 | Done | 2022-11-10 | 2022-11-14 | 3 | 0 | FALSE
|  | Write Integration test (Report 5) | 3 | ThanhNPN | 2022-11-10 | 2022-11-13 | Done | 2022-11-12 | 2022-11-14 | 2 | -1 | FALSE
| [UC-20] User Manage account | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 2 | DangHH | 2022-11-11 | 2022-11-11 | Done | 2022-11-11 | 2022-11-11 | 4 | 2 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 3 | ThanhNPN | 2022-11-11 | 2022-11-11 | Done | 2022-11-11 | 2022-11-11 | 4 | 1 | FALSE
|  | Coding Backend | 6 | SangDT | 2022-11-11 | 2022-11-13 | Done | 2022-11-11 | 2022-11-14 | 5 | -1 | FALSE
|  | Coding Frontend | 6 | SangDT | 2022-11-11 | 2022-11-13 | Done | 2022-11-11 | 2022-11-14 | 5 | -1 | FALSE
|  | Write Unit test (Report 5) | 3 | LongTT | 2022-11-13 | 2022-11-15 | Done | 2022-11-14 | 2022-11-16 | 2 | -1 | FALSE
|  | Write Integration test (Report 5) | 3 | ThanhNPN | 2022-11-13 | 2022-11-15 | Done | 2022-11-14 | 2022-11-15 | 3 | 0 | FALSE
| [UC-21] Manage all posting | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 2 | DangHH | 2022-11-13 | 2022-11-13 | Done | 2022-11-13 | 2022-11-13 | 3 | 1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 3 | ThanhNPN | 2022-11-13 | 2022-11-13 | Done | 2022-11-13 | 2022-11-13 | 3 | 0 | FALSE
|  | Coding Backend | 6 | LongTT | 2022-11-13 | 2022-11-15 | Done | 2022-11-13 | 2022-11-15 | 7 | 1 | FALSE
|  | Coding Frontend | 6 | LongTT | 2022-11-13 | 2022-11-15 | Done | 2022-11-13 | 2022-11-15 | 7 | 1 | FALSE
|  | Write Unit test (Report 5) | 3 | SangDT | 2022-11-15 | 2022-11-18 | Done | 2022-11-15 | 2022-11-18 | 3 | 0 | FALSE
|  | Write Integration test (Report 5) | 3 | ThanhNPN | 2022-11-15 | 2022-11-18 | Done | 2022-11-16 | 2022-11-19 | 2 | -1 | FALSE
| [UC-22] Manage category | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 4 | SangDT | 2022-11-15 | 2022-11-15 | Done | 2022-11-15 | 2022-11-15 | 4 | 0 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 4 | SangDT | 2022-11-15 | 2022-11-15 | Done | 2022-11-15 | 2022-11-16 | 5 | 1 | FALSE
|  | Coding Backend | 6 | DangHH | 2022-11-15 | 2022-11-17 | Done | 2022-11-15 | 2022-11-18 | 5 | -1 | FALSE
|  | Coding Frontend | 6 | LongTT | 2022-11-15 | 2022-11-17 | Done | 2022-11-15 | 2022-11-18 | 5 | -1 | FALSE
|  | Write Unit test (Report 5) | 4 | SangDT | 2022-11-18 | 2022-11-21 | Done | 2022-11-18 | 2022-11-22 | 3 | -1 | FALSE
|  | Write Integration test (Report 5) | 4 | ThanhNPN | 2022-11-18 | 2022-11-21 | Done | 2022-11-19 | 2022-11-21 | 4 | 0 | FALSE
| [UC-23] Mange all account User and Manager | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 3 | LongTT | 2022-11-17 | 2022-11-17 | Done | 2022-11-17 | 2022-11-18 | 1 | -2 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 5 | DangHH | 2022-11-17 | 2022-11-18 | Done | 2022-11-17 | 2022-11-19 | 4 | -1 | FALSE
|  | Coding Backend | 8 | DangHH | 2022-11-17 | 2022-11-21 | Done | 2022-11-17 | 2022-11-22 | 7 | -1 | FALSE
|  | Coding Frontend | 8 | LongTT | 2022-11-17 | 2022-11-21 | Done | 2022-11-17 | 2022-11-22 | 7 | -1 | FALSE
|  | Write Unit test (Report 5) | 4 | DangHH | 2022-11-21 | 2022-11-24 | Done | 2022-11-22 | 2022-11-24 | 5 | 1 | FALSE
|  | Write Integration test (Report 5) | 4 | ThanhNPN | 2022-11-21 | 2022-11-24 | Done | 2022-11-22 | 2022-11-25 | 5 | 1 | FALSE
| [UC-24] Statistics and Report | [10 empty] | TRUE
|  | Update Feature requirement (report 3) | 3 | ThanhNPN | 2022-11-21 | 2022-11-21 | Done | 2022-11-21 | 2022-11-22 | 2 | -1 | FALSE
|  | Create wireframe & Update Screen Details (report 3) | 3 | LongTT | 2022-11-21 | 2022-11-21 | Done | 2022-11-21 | 2022-11-21 | 4 | 1 | FALSE
|  | Coding Backend | 6 | SangDT | 2022-11-21 | 2022-11-25 | Done | 2022-11-21 | 2022-11-27 | 4 | -2 | FALSE
|  | Coding Frontend | 6 | ThanhNPN | 2022-11-21 | 2022-11-25 | Done | 2022-11-21 | 2022-11-26 | 5 | -1 | FALSE
|  | Write Unit test (Report 5) | 3 | LongTT | 2022-11-24 | 2022-11-27 | Done | 2022-11-25 | 2022-11-28 | 2 | -1 | FALSE
|  | Write Integration test (Report 5) | 4 | ThanhNPN | 2022-11-24 | 2022-11-27 | Done | 2022-11-26 | 2022-11-28 | 3 | -1 | FALSE
Report 1: Project Introduction |  |  | 10 | DangHH | 2022-09-08 | 2022-09-11 | Done | 2022-09-08 | 2022-09-11 | 12 | 2 | FALSE
| Review Report 1 |  | 3 | All | 2022-09-08 | 2022-09-11 | Done | 2022-09-08 | 2022-09-11 | 3 | 0 | FALSE
Report 2: Project Management Plan |  |  | 8 | ThanhNPN | 2022-09-11 | 2022-09-25 | Done | 2022-09-13 | 2022-12-05 | 7 | -1 | FALSE
| WBS |  | 15 | ThanhNPN | 2022-09-11 | 2022-09-25 | Done | 2022-09-13 | 2022-12-31 | 17 | 2 | FALSE
| Review Report 2 |  | 4 | All | 2022-09-24 | 2022-09-25 | Done | 2022-12-13 | 2022-12-31 | 4 | 0 | FALSE
Report 3: Software Requirement Specification | [11 empty] | TRUE
| Create report 3 outline |  | 2 | LongTT | 2022-09-12 | 2022-10-09 | Done | 2022-09-25 | 2022-10-09 | 3 | 1 | FALSE
| 1. Product Overview |  | 4 | LongTT | 2022-09-12 | 2022-10-09 | Done | 2022-09-25 | 2022-11-20 | 3 | -1 | FALSE
| 2. User Requirements |  | 15 | LongTT | 2022-09-12 | 2022-10-09 | Done | 2022-09-25 | 2022-11-20 | 14 | -1 | FALSE
| 3.1.1&2 Define screens flow & Screen Descriptions |  | 5 | LongTT | 2022-09-12 | 2022-10-09 | Done | 2022-09-25 | 2022-11-20 | 4 | -1 | FALSE
| 3.1.3&4 & Screen Authorization & Non screen functions |  | 5 | ThanhNPN | 2022-09-12 | 2022-10-09 | Done | 2022-09-25 | 2022-10-09 | 6 | 1 | FALSE
| 3.1.5ERD & Entity Description |  | 8 | LongTT | 2022-09-12 | 2022-10-09 | Done | 2022-09-25 | 2022-11-20 | 7 | -1 | FALSE
| 4. Non-function Requirements |  | 4 | SangDT | 2022-09-12 | 2022-10-09 | Done | 2022-09-25 | 2022-10-09 | 4 | 0 | FALSE
| 5.1 Business rule |  | 4 | SangDT | 2022-09-12 | 2022-10-09 | Done | 2022-09-25 | 2022-10-09 | 4 | 0 | FALSE
| 5.2-3 common requirements & Application Message List |  | 4 | LongTT | 2022-09-12 | 2022-10-09 | Done | 2022-09-25 | 2022-11-20 | 3 | -1 | FALSE
Report 4: Software Design Document | [11 empty] | TRUE
| Create report 4 outline |  | 4 | DangHH | 2022-10-03 | 2022-10-23 | Done | 2022-10-09 | 2022-10-24 | 3 | -1 | FALSE
| 1.1 System Architecture |  | 4 | DangHH | 2022-10-03 | 2022-10-23 | Done | 2022-10-10 | 2022-10-14 | 5 | 1 | FALSE
| 1.2 Package diagram |  | 6 | DangHH | 2022-10-03 | 2022-10-23 | Done | 2022-10-13 | 2022-10-25 | 3 | -3 | FALSE
| 1.2 Package diagram |  | 4 | DangHH | 2022-10-03 | 2022-10-23 | Done | 2022-10-15 | 2022-10-16 | 6 | 2 | FALSE
| 2.1 Database Diagram |  | 8 | DangHH | 2022-10-03 | 2022-10-23 | Done | 2022-10-16 | 2022-10-24 | 7 | -1 | FALSE
| 2.1 Database Diagram |  | 10 | ThanhNPN | 2022-10-03 | 2022-10-23 | Done | 2022-10-10 | 2022-10-24 | 9 | -1 | FALSE
| Review Database Design |  | 10 | SangDT | 2022-10-03 | 2022-10-23 | Done | 2022-10-10 | 2022-10-24 | 7 | -3 | FALSE
| 2.2 Table Descripton |  | 10 | ThanhNPN | 2022-10-03 | 2022-10-23 | Done | 2022-10-13 | 2022-10-25 | 7 | -3 | FALSE
| 3.1 Class diagram |  | 8 | SangDT | 2022-10-03 | 2022-10-23 | Done | 2022-10-15 | 2022-10-23 | 10 | 2 | FALSE
Report 5: Software Test Documentation | [11 empty] | TRUE
| 1. Scope of testing |  | 5 | DangHH | 2022-10-09 | 2022-11-27 | Done | 2022-10-09 | 2022-11-28 | 4.5 | -0.5 | FALSE
| 2. Test strategy |  | 5 | ThanhNPN | 2022-10-09 | 2022-11-27 | Done | 2022-10-09 | 2022-11-28 | 3.5 | -1.5 | FALSE
| 3. Test plan |  | 5 | ThanhNPN | 2022-10-09 | 2022-11-27 | Done | 2022-10-09 | 2022-11-28 | 4.5 | -0.5 | FALSE
| 5. Test Reports |  | 5 | DangHH | 2022-10-09 | 2022-11-27 | Done | 2022-10-09 | 2022-11-29 | 3 | -2 | FALSE
Report 6: Software User Guides | [11 empty] | TRUE
| 1 .Deliverable package |  | 4 | LongTT | 2022-11-13 | 2022-12-04 | Done | 2022-11-23 | 2022-12-01 | 3 | -1 | FALSE
| 2. Installation guides |  | 4 | SangDT | 2022-11-13 | 2022-12-04 | Done | 2022-11-24 | 2022-12-01 | 5 | 1 | FALSE
| 3. User manual overview |  | 5 | SangDT | 2022-11-13 | 2022-12-04 | Done | 2022-11-26 | 2022-12-03 | 4 | -1 | FALSE
| 3. User manual |  | 8 | LongTT | 2022-11-13 | 2022-12-04 | Done | 2022-11-28 | 2022-12-03 | 10 | 2 | FALSE
Report 7: Final Project Report | [11 empty] | TRUE
| Collect and fix report 1 |  | 4 | All | 2022-12-02 | 2022-12-05 | Done | 2022-12-02 | 2022-12-04 | 4 | 0 | FALSE
| Collect and fix report 2 |  | 4 | All | 2022-12-02 | 2022-12-05 | Done | 2022-12-02 | 2022-12-04 | 4 | 0 | FALSE
| Collect and fix report 3 |  | 4 | All | 2022-12-02 | 2022-12-05 | Done | 2022-12-02 | 2022-12-04 | 2 | -2 | FALSE
| Collect and fix report 4 |  | 4 | All | 2022-12-02 | 2022-12-05 | Done | 2022-12-02 | 2022-12-04 | 3 | -1 | FALSE
| Collect and fix report 5 |  | 4 | All | 2022-12-02 | 2022-12-05 | Done | 2022-12-02 | 2022-12-04 | 3 | -1 | FALSE
| Collect and fix report 6 |  | 4 | All | 2022-12-02 | 2022-12-05 | Done | 2022-12-02 | 2022-12-04 | 3 | -1 | FALSE
Deployment | [11 empty] | TRUE
| Create pipeline for Staging |  | 6 | SangDT | 2022-11-27 | 2022-12-04 | Done | 2022-12-02 | 2022-12-02 | 2 | -4 | FALSE
| CI/CD pipeline for Dev |  | 12 | SangDT | 2022-11-27 | 2022-12-04 | Done | 2022-12-03 | 2022-12-04 | 20 | 8 | FALSE
| Set up azure account & subscription |  | 8 | SangDT | 2022-11-27 | 2022-12-04 | Done | 2022-12-03 | 2022-12-04 | 4 | -4 | FALSE

## Tracking
P.I.C | Total Effort (h) | Total Actual (h)
All | 191 | 186
DangHH | 211 | 205
ThanhNPN | 215 | 209
SangDT | 222 | 216
LongTT | 203 | 188
Tổng cộng | 1042 | 1004

## EV etimate
Start Date | 2022-09-01
End Date | 2022-12-04
Today | 2022-12-05
Work per day per mem | 6 | h
Work per week per mem | 42
Team size | 4
Calendar Effort | 1608 | h
Actual Cost | 8704
Plan Value | 1018 | h
Earn Value | 1042 | h
Total Work To Do | 1042 | h
Remaing Works Plan | 0 | h
Working Plan | 0 | h
Remaining Effort | 0 | h
Works Done | 190 | Task
Work plan | 190
Percent Done | 100%